14 June 05

Bristol Electric Railbus Long Meadow House Marford Bridge Cory-Wright Way Wheathampstead Herts AL4 8ND For the attention of Mr Renshaw Watts

Dear Sirs,

Re -Luton: Ultra Light Rail System.

Thank you for your email dated the 10/June/05 requesting further information and pricing, we are currently resource constrained and cannot spend the time that your request warrants, however we have produced an order of magnitude guide price.

This price you should take as our best estimate based on a one day walk through and our experience from other light rail systems.

AMEC has the capability to undertake all of these works including the Project Management and design for this project, and would be delighted to discuss undertaking this project with yourselves

I hope everything goes well with your presentation to the enquiry and look forward to taking this opportunity through to fulfilment.

Yours Sincerely

Peter Holland

Senior Project Manager

AMEC SPIE Rail (UK) Ltd

Table of order of magnitude pricing for the Luton – Dunstable pre-feasibility phase

| Element | Cost | Comment |
| --- | --- | --- |
| Pway cost | £ 4,250,000 | as previously advised |
| Pway Costs for second line | £ 3,000,000 | Making allowance for extra S/C, Road crossings Bi directional working etc |
| Electrification | £ 2,000,000 | This should be sufficient to allow power for signalling, station, depot, CCTV, Passenger information system etc. |
| Signalling | £ 2,000,000 | This should allow for narrow bridge, road crossing, departure/arrival indication etc |
| Civils | £ 4,000,000 | This should allow for required works to cuttings, embankments, station surrounds and the disposal of a reasonable quantity of contaminated waste. |
| Design | £ 4,000,000 | To allow for soil investigation, all permissions, consents and certifications, liaison with third parties including HMRI, as built records, CDM, HSEQ etc |
| Sub - Total | £ 19,250,000 |  |
| Project Management | £ 1,900,000 |  |
| Contingency | £ 3,850,000 |  |
| Total Cost | £ 25,000,000 |  |

Excludes

Fuel Storage

Consultant Costs

Client Costs

Other third party costs (HMRI etc)

Vehicles

Land Acquisition

Bridge investigation and works arising

Required Highway changes and road closures

Feasibility Study

The term feasibility study can mean different things to different people, our indicative price includes for

- Soil Investigations including Laboratory analysis to determine level of contamination

- A review of the Environmental reports

- Proposed layout of track, signalling, Electrification, Telecomms, Civils

- Liaison with all third parties such that consent in principle are granted

- Material Take offs undertaken with pricing to gain an accurate view of the remainder of the project and if required an indicative maintenance cost

- Pre construction Health and Safety Plan

The cost for the above Approximately £ 2,000,000 duration up to 5 months depending how long it takes to mobilise the soil investigation team and receive the completed laboratory analysis. This is also assuming that the work can continue into detail design and ordering of any long lead items.

We recommend that a bridge inspection is undertaken at the same time, which AMEC can manage, thus ensuring that the feasibility study ends with an all inclusive finalised cost.

The above excludes all public enquiries, liaison with the public and works associated with land acquisition